## Cover sheet
QC/QA Concrete Pavement Construction Checklist
Date
Project Number
Contract Number
Paving Contractor
Field Office
Contract Specifications that apply to QC/QA Concrete Paving
Division 150 Equipment
Section 152
Section 154
Division 400 Concrete
Special Provision number
Special Provision number
Division 500 Rigid Pavement
Special Provision number
Special Provision number
Special Provision number
Division 1100 Aggregates
Special Provision number
Special Provision number
Special Provision number
Special Provision number

## Inspectors
Certifications
Inspection Personnel |  | Inspector Number
Responsible for
Certifications
BI | Basic Inspection
AGF | Aggregate Field Tester
AGL | Aggregate Lab Technician
PO | Profilograph
CF | ACI Concrete Field Technician
NUC | Nuclear Density Gauge Tester
HCP | Hardened Concrete Properties
QCS | QC/QA Concrete /Cement Treated Base Specs
Proper certifications for work performed?
Certifications expire before end of project?
Note on A3: This is to be completed for each inspector and tester on the project for the contractor, consultant and KDOT

## Mix Design Approval
Mix Design Approval
Does the mix meet the MA requirements in the specification
Is there a completed form 649 for each mix design
Are there mix designs for all concrete types of pavement
Are the aggregate sources prequalified
Check the aggregate sources prequalification's periodically for
duration of project
Are the cement/cementitious materials prequalified
Does the mix design meet the permeability requirements for
which of the following permeability test. This test will be used
for verification of the mix design
KT 73
KT 79
AASHTO T-277
Does the mix design meet he requirements for compressive
strength
Is there previous data that meets the requirements for the
specification
Has mix design been used in last 12 months
Are materials for mix design from the same sources as
previous mix design
If no data does the mix design meet the minimum
requirements in the specification of 5200 psi?
Does concrete mix include supplemental cementitious
material?
Mortar expansion test results ASTM C 1567 shall be part of
the mix design according to table in specification
Are the admixtures on the PQL
Is the mix design in CMS/AASHTOWARE?
Was the test batch made at the max water/cement ratio

## Laboratory
Laboratory Testing
Testing
Has QC/QA plan been approved by DME?
All testing equipment been calibrated and documented?
|  |  | Date Calibrated | Date Expire
Compression Testing Equipment/Breakers
Scales
Thermometers
Shakers/Sieves
Field Testing Equipment (Air/Slump/Weight)
Nuclear Gage
Profilograph
Other Equipment
Has AVA been performed at beginning and once every 4 weeks of production
Have trucks beds been inspected
Is all water in the drum after first 15 seconds of mixing
Is the rated capacity of mixer being exceeded
Is the mixing time between 1 and 5 minutes
If a high performance mixing drum is used time may be reduced under a minute based on requirements in specification
Have the moisture tests been done
Company organization chart posted
Are all test results made available daily
Are all test results documented in a bound book or source approved by DCE/DME
Test being completed in accordance with QC/QA plan and specifications and frequencies in part V being followed
Will testing frequencies be changed
Yes
Has DME approved
Yes
No
Are last 10 gradations retained
Is field inspector performing air, slump, weight test?
If not perform test as required
Lot Size Determination
Lot size determined according to specification
Thickness and Strength
Thickness only
Lot size determined as Urban
No
Yes
Thickness and Strength
Thickness only
Determine lot size according to specification
Does project have bonus for smoothness
Have profilograms been giving within two days
Is the correct spreadsheet being used
Cores
Random locations determined for the cores
Taken on the correct day
Record Keeping
Daily Cement
Daily Aggregates
Daily Admixtures
Daily Square Yards
Test entered in CMS/AASHTOWARE

## Paving
Paving Inspection
Vibrators frequency checked before starting paving
Paving equipment checked for leaks
Is plant inspector performing air, slump, weight tests
If not perform test as required
Subgrade been prepared as required by specification
Has subgrade been moistened before placement of concrete
Is the stringline set according to specification
Stringless is the GPS used for horizontal control and total station
used for vertical control
Is reinforcement placed according to contract documents and
held in place according to specification
Have the dowel baskets been cut
Is the reinforcement the correct size and location
Are tie bars secure
If tie bars are placed mechanically are random checks being made
for depth and location daily
Are the forms set according to specification
Is concrete being placed within time requirement
Is concrete being correctly vibrated for fixed form placement
Are vibrators being checked every 4 hours of mainline paving
Grooving equipment meet the requirements in the specification
Is the concrete being grooved to early/late
Cure being applied at the correct rate of 1 gal per 150 square feet
and time? Is this verified and documented
Are all joints being sawed (longitudinal/transverse) as soon
as concrete has hardened
Is slurry being immediately removed from joint after saw cut
Joints properly cleaned before application of sealant
Profilograms been given to KDOT before opening to traffic
Concrete specifications been met before opening to traffic
Daily Checks
Thickness documented
Slope documented
Vibrator checks documented

## Testing
Testing
Air Void analyzer at beginning of project and once every four weeks
Air/Slump/Weight being correctly tested
Moisture in aggregate being tested daily
Correct gradations being completed
Is project determined as Urban
Are lots correct size
Profilograph
Is profilograph being used properly certified
Profilograms received within 2 days of pavement placement
Pay adjustments for smoothness calculated before corrections
Strength
Thickness