## RFP List
RFP Group | Anticipated Advertisement Date | RFP Due Date | Managing Office | Route - County | Project # | Anticipated Const Start | Working Days | Cal Comp Date | Scope of Project | Scope of Services Requested | Project Location | Comments
24417 | 1/16/25 | 2025-02-05 | Iola | U059- 001 | KA-7529-01 |  | 40 |  | Ultra-thin Bonded Asphalt Surfacing (UBAS), rumble strips and thermo striping | Project Manager and inspectors as necessary to inspect: HMA Plant, HMA Roadway, Traffic Control, AASHTOWare data entry, all Project Records, all Project Paperwork and Final Paperwork, etc. | US-59 in Allen county beginning at the Neosho/Allen county line, north to the Allen/Anderson county line
24418 | 1/16/25 | 2025-02-05 | Iola | K058- 106 | KA-7570-01 |  | 30 |  | 1 inch cold milling and 1.5 inch overlay | Project Manager and inspectors as necessary to inspect: HMA Plant, HMA Roadway, Traffic Control, AASHTOWare data entry, all Project Records, all Project Paperwork and Final Paperwork, etc. | KA-7571-01: K-58 in Coffey county beginning at the west city limits of LeRoy to the Coffey/Anderson county line. KA-7572-01: K-58 in Anderson county beginning at the Coffey/Anderson county line to the US-169/K-58 junction.
24419 | 1/16/25 | 2025-02-05 | Iola | K058- 016 | KA-5701-01 |  | 160 |  | Bridge replacement | Project Manager and inspectors as necessary to inspect: Grading, Subgrade/Base, Concrete, Bridge, HMA Roadway, Seeding, Erosion Control Traffic Control, AASHTOWare data entry, all Project Records, all Project Paperwork and Final Paperwork, etc. | K-58: Bridge #043 over Crooked Creek located 6.68 miles east of the south U.S. 75/K-58 junction
24420 | 1/16/25 | 2025-02-05 | Iola | K031- 054 | KA-7561-01 |  | 50 |  | 1.5 inch overlay and edge wedge | Project Manager and inspectors as necessary to inspect: HMA Plant, HMA Roadway, pavement patching Traffic Control, AASHTOWare data entry, all Project Records, all Project Paperwork and Final Paperwork, etc. | KA-7562-01: K-31 in Bourbon county beginning at the Bourbon/Linn county line to the K-65/K-31 junction. KA-7563-01: K-31 in Linn county beginning at the K-52/K-31 junction to the Linn/Bourbon county line.
24421 | 1/16/25 | 2025-02-05 | Independence | U160- 025 | KA-6969-01 | 2025-04-01 | 110 |  | Patching, overlay, replace rail, drip edge repair, joints, guardrail update | Project Manager and inspectors as necessary to inspect: Grading, Pavement Patching, Concrete, Bridge, Seeding, Erosion Control Traffic Control, AASHTOWare data entry, all Project Records, all Project Paperwork and Final Paperwork, etc. | Bridge #008 (Elk River) located 5.86 miles East of the East Junction of US-160 and K-99
24607 | 1/16/25 | 2025-02-05 | Liberal | U083- 041 | KA-1008-02 |  | 220 |  | 2-Lane pavement reconstruction based on a 44 ft. roadway, including 10 ft shoulders, on an offset alignment. Project will include the addition of passing lanes as warranted. Purchase Right of Way for a future 4-Lane Expressway section with partial acces | Project Manager and inspectors as necessary to inspect: Grading, Subgrade/Base, HMA Plant, HMA Roadway, Seeding, Erosion Control, Traffic Control, AASHTOWare data entry, all Project Records, all Project Paperwork and Final Paperwork, etc. | US-83: from Sublette north to 1.75 mile south of the junction of US-83/US-160.
24422 | February |  | Independence | U075- 103 | KA-6782-01 | 2025-04-14 | 235 |  | Bridge #034: Deck Patch and Overlay, New Overhang/Rail, New 33 ft Approach Slabs, New Edge Wearing Surface Joints and Slope Drains. Culvert #530: Replacement | Project Manager and inspectors as necessary to inspect: Grading, Pavement Patching, Subgrade/Base, HMA Roadway, Concrete, Bridge, Seeding, Erosion Control Traffic Control, permanent pavement marking and signing, AASHTOWare data entry, all Project Records, all Project Paperwork and Final Paperwork, etc. | US-75: Bridge #034 (Verdigris River) located 2.3 Miles North of North Junction US-400/US-75 and Culvert #530 (Verdigris River Drainage) located 2.1 Miles East of US-75/US-400
24423 | February |  | Independence | U160- 063 | KA-6958-01 | 2025-04-07 | 160 |  | Replace guardrail and grind approaches | Project Manager and inspectors as necessary to inspect: Grading, Pavement Patching, Subgrade/Base, HMA Roadway, Concrete, Bridge, Seeding, Erosion Control, Permanent Pavement marking and signing, Traffic Control, AASHTOWare data entry, all Project Records, all Project Paperwork and Final Paperwork, etc. | Bridge #066 (Big Hill Creek) on U.S. 160 in Montgomery county located 1.99 mile east of U.S. 169
25101 | February |  |  | -106 | KA-7454-01 | 2025-03-15 | 55 |  | Construct infrastructure for installation of 11 Continuously Operating Reference Stations | Project Manager and inspectors as necessary to inspect: CORS Inspection AASHTOWare data entry, all Project Records, all Project Paperwork and Final Paperwork, etc. | Statewide | Multiple sites across the state
25102 | February |  | Bonner Springs | -106 | KA-7238-01 | 2025-03-15 | 65 |  | Sidewalks | Project Manager and inspectors as necessary to inspect: Concrete, Seeding, Erosion Control AASHTOWare data entry, all Project Records, all Project Paperwork and Final Paperwork, etc. | City of Whiting (Jackson County), City of Leavenworth (Leavenworth County), City of Garnett (Anderson County), City of Edna (Labette County), City of Kinsley (Edwards County)
25103 | February |  | Wamego | U077- 058 | KA-7503-01 |  | 60 |  | 2 inch Hot In-place Recycle (HIR) and chip seal | Project Manager and inspectors as necessary to inspect: HMA Plant, HMA Roadway, Pavement Marking, Traffic Control, AASHTOWare data entry, all Project Records, all Project Paperwork and Final Paperwork, etc. | US-77 in Marshall county beginning at the US-77/K-9 west junction, east and north to the south city limits of Marysville
25103 | February |  | Wamego | K009- 058 | KA-7502-01 |  | 60 |  | 2 inch Hot In-place Recycle (HIR) and chip seal | Project Manager and inspectors as necessary to inspect: HMA Plant, HMA Roadway, Pavement Marking, Traffic Control, AASHTOWare data entry, all Project Records, all Project Paperwork and Final Paperwork, etc. | K-9 in Marshall county beginning at the Washington/Marshall county line, east to the US-77/K-9 west junction
25103 | February |  | Wamego | K099- 058 | KA-7544-01 |  | 40 |  | 0.75 inch cold milling, 2 inch overlay and edge wedge | Project Manager and inspectors as necessary to inspect: HMA Plant, HMA Roadway, Pavement Marking, Traffic Control, AASHTOWare data entry, all Project Records, all Project Paperwork and Final Paperwork, etc. | K-99 in Marshall county beginning at the K-99/US-36 junction, north to the Kansas/Nebraska state line
25103 | February |  | Wamego | U036- 058 | KA-7566-01 |  | 40 |  | 1 inch cold milling and 1.5 inch overlay from county line to the 4 lane divide/4 lane. 1.5 inch cold milling and 1.5 inch overlay from the 4 lane divide/4 lane, east to 4th Street in Marysville | Project Manager and inspectors as necessary to inspect: HMA Plant, HMA Roadway, Pavement Marking, Traffic Control, AASHTOWare data entry, all Project Records, all Project Paperwork and Final Paperwork, etc. | US-36 in Marshall county beginning at the Marshall/Osborne county line, east to 4th Street in Marysville
25104 | February |  | Bonner Springs | K005- 105 | KA-7472-01 |  | 45 |  | 2 inch cold milling, 2 inch overlay and rumble strips on shoulders | Project Manager and inspectors as necessary to inspect: Grading, HMA Plant, HMA Roadway, Pavement Patching, Edge Wedge, Traffic Control, AASHTOWare data entry, all Project Records, all Project Paperwork and Final Paperwork, etc. | K-5 in Wyandotte county beginning at the I-635/K-5 junction east to the McCormick Road/Sunshine Road junction
25104 | February |  | Bonner Springs | K016- 106 | KA-7469-01 | 2025-04-14 | 50 |  | 1 inch cold milling, 1.5 inch overlay, edge wedge and rumble strips on centerline and shoulders | Project Manager and inspectors as necessary to inspect: Grading, HMA Plant, HMA Roadway, Pavement Patching, Edge Wedge Traffic Control, AASHTOWare data entry, all Project Records, all Project Paperwork and Final Paperwork, etc. | KA-7470-01: K-16 in Jefferson county - K-92/K-16 junction in McLouth, east to the Leavenworth/Jefferson county line. KA-7471-01: K-16 in Leavenworth county - Leavenworth/Jefferson county line, southeast to the US-24/K-16/US-40 junction
25105 | February |  | Bonner Springs | U024- 023 | KA-7512-01 |  | 95 |  | 1 inch cold milling, 1.5 inch overlay, edge wedge and rumble strips on centerline and shoulders | Project Manager and inspectors as necessary to inspect: Grading, HMA Plant, HMA Roadway, Pavement Patching, Edge Wedge Traffic Control, AASHTOWare data entry, all Project Records, all Project Paperwork and Final Paperwork, etc. | US-24 in Douglas county beginning at the Jefferson/Douglas county line, east to the Douglas/Leavenworth county line
25105 | February |  | Bonner Springs | U059- 044 | KA-7513-01 |  | 95 |  | 1 inch cold milling, 1.5 inch overlay, edge wedge and rumble strips on centerline and shoulders | Project Manager and inspectors as necessary to inspect: Grading, HMA Plant, HMA Roadway, Pavement Patching, Edge Wedge Traffic Control, AASHTOWare data entry, all Project Records, all Project Paperwork and Final Paperwork, etc. | US-59 in Jefferson county beginning at the US-24/US-59 junction, north to the south city limits of Oskaloosa
25105 | February |  | Bonner Springs | U024- 044 | KA-7510-01 |  | 95 |  | 1 inch cold milling, 1.5 inch overlay, edge wedge and rumble strips on centerline and shoulders | Project Manager and inspectors as necessary to inspect: Grading, HMA Plant, HMA Roadway, Pavement Patching, Edge Wedge, Traffic Control, AASHTOWare data entry, all Project Records, all Project Paperwork and Final Paperwork, etc. | US-24 in Jefferson county beginning at the Elm Street/US-24 junction in the city of Perry, east to the Jefferson/Douglas county line
25106 | February |  | Bonner Springs | I670- 105 | KA-7549-01 |  | 0 | 2025-09-26 | Portland Cement Concrete Pavement (PCCP) patching, grinding, saw and seal joints | Project Manager and inspectors as necessary to inspect: Pavement Patching, Concrete, PCCP Plant, Traffic Control, AASHTOWare data entry, all Project Records, all Project Paperwork and Final Paperwork, etc. | I-670 in Wyandotte county beginning at the I-670/I-70 junction, east to the Kansas/Missouri state line | night work, March Letting
25106 | February |  | Bonner Springs | I070- 105 | KA-7550-01 |  | 0 | 2025-09-26 | Portland Cement Concrete Pavement (PCCP) patching, grinding, saw and seal joints | Project Manager and inspectors as necessary to inspect: Pavement Patching, Concrete, PCCP Plant, Traffic Control, AASHTOWare data entry, all Project Records, all Project Paperwork and Final Paperwork, etc. | I-70 in Wyandotte county beginning 0.1 mile west of 7th Street, east to the Kansas/Missouri state line | March Letting, night work,
25107 | February |  | Bonner Springs | I070- 105 | KA-7548-01 |  | 0 | 2025-09-21 | Portland Cement Concrete Pavement (PCCP) patching, grinding, saw and seal joints | Project Manager and inspectors as necessary to inspect: HMA Plant, HMA Roadway, Pavement Patching, Concrete, PCCP Plant, Traffic Control, AASHTOWare data entry, all Project Records, all Project Paperwork and Final Paperwork, etc. | I-70 in Wyandotte county beginning east of east approach of bridge #211 and #212 over ramps to eastbound I-70/I-435, east to 0.28 mile west of 78th Street | March Letting, night work
25201 | February |  | Belleville | U081- 079 | KA-7374-01 |  | 35 |  | Hot surface recycle and chip seal PLEASE SEE PROJECT AUTHORIZATIONS NOTES FOR MORE DETAILS | Project Manager and inspectors as necessary to inspect: Chip Seal Traffic Control, AASHTOWare data entry, all Project Records, all Project Paperwork and Final Paperwork, etc. | US-81 in Republic county beginning 3.16 miles north of the US-36/US-81 junction, north to northeast state line
25201 | February |  | Belleville | -106 | KA-7401-01 |  | 35 |  | KA-7402-01 and KA-7403-01: 1.5 inch hot in-place surface recycling and chip seal. KA-7404-01: chip seal | Project Manager and inspectors as necessary to inspect: HMA Roadway, Traffic Control, AASHTOWare data entry, all Project Records, all Project Paperwork and Final Paperwork, etc. | KA-7402-01 thru KA-7404-01: See project authorization notes
25202 | February |  | Belleville | U036- 079 | KA-7382-01 | 2025-05-05 | 45 |  | 1.5 inch milling and overlay | Project Manager and inspectors as necessary to inspect: HMA Plant, HMA Roadway, Traffic Control, AASHTOWare data entry, all Project Records, all Project Paperwork and Final Paperwork, etc. | US-36 in Republic county beginning at the Jewell/Republic county line, east to 0.36 mile east of the US-36/US-81
25301 | February |  | Atwood | K027- 091 | KA-6123-01 | 2025-06-02 | 95 |  | Concrete Overlay, Patch Deck, Replace Rails, Replace Approach Slabs | Project Manager and inspectors as necessary to inspect: Concrete, Bridge Repair and Overlay, Traffic Control, AASHTOWare data entry, all Project Records, all Project Paperwork and Final Paperwork, etc. | K-27: Bridge #042 over the Kyle Railroad located 0.84 mile north of I-70
25302 | February |  | Oakley | K027- 100 | KA-6778-01 | 2025-05-01 | 0 | 2025-10-31 | New Approaches, Machine Prep, Deck patch, and Overlay, New Overhang and Rail (curb at Piers), New Joints, Add Joint Drains, Repair Pier Caps, upgrade guardrail | Project Manager and inspectors as necessary to inspect: Concrete, Bridge Repair and Overlay, Traffic Control, AASHTOWare data entry, all Project Records, all Project Paperwork and Final Paperwork, etc. | Bridge #017 over Smoky Hill River on K-27 in Wallace County
25303 | February |  | Oakley | K023- 090 | KA-5756-01 | 2025-07-01 | 210 |  | Bridge Replacement | Project Manager and inspectors as necessary to inspect: Grading, HMA Roadway, Concrete, Bridge, Seeding, Erosion Control, Traffic Control, AASHTOWare data entry, all Project Records, all Project Paperwork and Final Paperwork, etc. | Bridge #019 (North Fork Solomon River) on K-23 in Sheridan County located 3.22 miles South of junction K-123/K-23
25304 | February |  | Oakley | I070- 097 | KA-7445-01 | 2025-03-24 | 80 |  | 2 inch milling and inlay mainline. 1.5 inch overlay on mainline, shoulders, ramps and crossovers | Project Manager and inspectors as necessary to inspect: HMA Plant, HMA Roadway, Rumble Strips, Edge Wedge, Pavement Marking, Traffic Control, AASHTOWare data entry, all Project Records, all Project Paperwork and Final Paperwork, etc. | I-70 in Thomas county from just east of County Road K (Exit 62), southeast 11.96 miles to the Thomas/Logan county line
25401 | February |  | Iola | K007- 006 | KA-5804-01 |  | 0 | 2027-06-18 | Rehabilitate roadway, add six (6) foot wide composite shoulders and replace Little Pawnee Creek Drainage bridge #030 | Project Manager and inspectors as necessary to inspect: Grading, HMA Plant, HMA Roadway, Subgrade/Base, Concrete, Bridge, Seeding, RC Boxes, Erosion Control Traffic Control, AASHTOWare data entry, all Project Records, all Project Paperwork and Final Paperwork, etc. | K-7: Beginning at the Crawford/Bourbon county line north to 0.4 mile southwest of U.S. 69 (includes Little Pawnee Creek Drainage bridge #030 | February letting
25401 | February |  | Pittsburg | K007- 019 | KA-5803-02 |  | 0 | 2027-06-18 | Rehabilitation, add six (6) foot composite shoulders, replace culvert #513 over Second Cow Creek Drainage | Project Manager and inspectors as necessary to inspect: Grading, HMA Plant, HMA Roadway, Subrgrade/Base, Concrete, Bridge, Seeding, RC Boxes, Erosion Control Traffic Control, AASHTOWare data entry, all Project Records, all Project Paperwork and Final Paperwork, etc. | K-7: beginning 0.962 mile north of West 700th Avenue to the Bourbon County line | February letting
25402 | February |  | Garnett | U169- 061 | KA-7484-01 |  | 55 |  | Ultra-thin Bonded Asphalt Surfacing (UBAS) and thermo striping | Project Manager and inspectors as necessary to inspect: HMA Plant, HMA Roadway, Milling, Pavement Marking, Traffic Control, AASHTOWare data entry, all Project Records, all Project Paperwork and Final Paperwork, etc. | US-169 in Miami county beginning 0.77 mile south of the K-7/US-169 south junction, north to 1.42 miles south of the Miami/Johnson county line
25402 | February |  | Garnett | K279- 061 | KA-7485-01 |  | 55 |  | Ultra-thin Bonded Asphalt Surfacing (UBAS) and thermo striping | Project Manager and inspectors as necessary to inspect: HMA Plant, HMA Roadway, Milling, Pavement Marking, Traffic Control, AASHTOWare data entry, all Project Records, all Project Paperwork and Final Paperwork, etc. | K-279 in Miami county beginning at the US-169/K-279 junction, north to State Hospital
25403 | February |  | Garnett | U069- 054 | KA-7543-01 |  | 35 |  | Ultra-thin Bonded Asphalt Surfacing (UBAS), thermo striping and rumble strips on centerline and shoulders | Project Manager and inspectors as necessary to inspect: HMA Plant, HMA Roadway, Traffic Control, AASHTOWare data entry, all Project Records, all Project Paperwork and Final Paperwork, etc. | US-69 in Linn county beginning 4.185 miles north of the K-52/US-69 south junction, north to 2.675 miles north of the K-52/US-69 north junction
25501 | February |  | El Dorado / Hutchinson | U050- 040 | KA-7460-01 | 2025-03-31 | 35 |  | 1.75 inch cold milling, 2 inch overlay and rumble strips on the centerline and shoulders | Project Manager and inspectors as necessary to inspect: HMA Plant, HMA Roadway, Milling, Pavement Marking, Rumble Strips Traffic Control, AASHTOWare data entry, all Project Records, all Project Paperwork and Final Paperwork, etc. | US-50 in Harvey county beginning at the Hot mix asphalt south of the I-135/US-50 junction, east to the Harvey/Marion county line
25502 | February |  | El Dorado / Hutchinson | U077- 008 | KA-7456-01 | 2025-05-05 | 35 |  | Ultra-thin bonded asphalt surfacing, thermo striping and rumble strips on centerline and shoulders | Project Manager and inspectors as necessary to inspect: Hma Plant, HMA Roadway, Milling, Pavement Marking, Rumble Strips Traffic Control, AASHTOWare data entry, all Project Records, all Project Paperwork and Final Paperwork, etc. | US-77 in Butler county beginning at the 4 lane to 4 lane divided, north to the Marion/Butler county line
25503 | February |  | Pratt | U281- 004 | KA-7430-01 | 2025-06-02 | 50 |  | 1.5 inch cold milling, 1.5 inch overlay and rumble strips on centerline and shoulders | Project Manager and inspectors as necessary to inspect: HMA Plant, HMA Roadway, Milling, Pavement Marking, Rumble Strips Traffic Control, AASHTOWare data entry, all Project Records, all Project Paperwork and Final Paperwork, etc. | US-281 in Barber county beginning at the Oklahoma/Kansas state line, north to the US-160/US-281 junction
25503 | February |  | Pratt | U160- 004 | KA-7429-01 | 2025-06-02 | 45 |  | 1.5 inch overlay and edge wedge | Project Manager and inspectors as necessary to inspect: HMA Plant, HMA Roadway, Milling, Pavement Marking, Edge Wedge Traffic Control, AASHTOWare data entry, all Project Records, all Project Paperwork and Final Paperwork, etc. | US-160 in Barber county beginning at the Barber/Comanche county line, east to the west edge wearing surface of bridge #041